## Cover
YAM Agri Platform V1.1
Work Breakdown Structure + Gantt Chart
Project | YAM Agri Platform — Quality + Traceability Core
Version | 1.0
Date | 2026-02-23
Owner | YasserAKareem
Status | Approved — Baseline Plan
Duration | 20 calendar weeks (2026-02-23 → 2026-07-10)
Total effort | ≈ 105 dev-days (1 developer + 1 DevOps + 1 QA)
Sheets | Cover ¦ WBS ¦ Gantt ¦ Backlog ¦ Milestones

## WBS
WBS ID | Work Package / Task | Owner | Effort (d) | Depends on | Notes | Execution Status | Status Updated On | Started On | Completed On | Schema | Validation | Permissions/Isolation | Workflow | Evidence
0 | Phase 0 — Dev Environment Setup |  |  |  |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.1 | Docker Compose stack design | DevOps | 1 | — |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.1.1 | Write docker-compose.yml (MariaDB/Redis/nginx) | DevOps | 1 | 0.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.1.2 | Service healthchecks + restart: always | DevOps | 0.5 | 0.1.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.1.3 | Tune memory ≤ 6 GB | DevOps | 0.5 | 0.1.2 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.2 | run.sh helper script | DevOps | 1.5 | 0.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.2.1 | up / down / logs / shell / init | DevOps | 1 | 0.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.2.2 | reset / backup / restore / prefetch / offline-init | DevOps | 0.5 | 0.2.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.3 | Offline image archive (offline-images.tar) | DevOps | 0.5 | 0.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.4 | Frappe + ERPNext + Frappe Agriculture install | DevOps | 1 | 0.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.4.1 | bench new-site + ERPNext install | DevOps | 0.5 | 0.4 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.4.2 | Frappe Agriculture app install + verify | DevOps | 0.5 | 0.4.1 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.5 | VS Code devcontainer.json | Dev | 0.5 | 0.4 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
0.6 | Phase 0 acceptance: stack < 5 min; login works | DevOps | 0.5 | 0.1–0.5 |  | Done | 2026-02-24 | 2026-03-06 | 2026-03-06 | ✅ | ✅ | ✅ | ✅ | ✅
1 | Phase 1 — Custom App Scaffolding |  |  |  |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.1 | bench new-app yam_agri_core | Dev | 0.5 | 0 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.2 | Module structure (YAM Agri Core module) | Dev | 0.5 | 1.1 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.3 | App hooks (hooks.py) — fixtures/scheduler/signals | Dev | 1 | 1.2 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.4 | Workspace setup (Frappe Desk workspace) | Dev | 0.5 | 1.2 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.5 | CI / GitHub Actions pipeline | DevOps | 1 | 1.1 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.5.1 | Lint (flake8, eslint) | DevOps | 0.5 | 1.5 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.5.2 | Secret scan (truffleHog) | DevOps | 0.5 | 1.5 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.5.3 | Unit test runner (pytest) | DevOps | 0.5 | 1.5 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.6 | requirements.txt + pyproject.toml base | Dev | 0.5 | 1.1 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
1.7 | Phase 1 acceptance: app installs; CI green | DevOps | 0.5 | 1.1–1.6 |  | Done | 2026-02-24 | 2026-03-13 | 2026-03-13 | ✅ | ✅ | ✅ | ✅ | ✅
2 | Phase 2 — Core DocTypes (12) |  |  |  |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.1 | Site DocType | Dev | 1 | 1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.1.1 | Fields: site_code / name / type / GPS / active | Dev | 0.5 | 2.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.1.2 | Permissions + User Permission link | Dev | 0.5 | 2.1.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.2 | StorageBin DocType | Dev | 1 | 2.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.3 | Device DocType | Dev | 1 | 2.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.4 | Lot DocType | Dev | 2 | 2.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.4.1 | Fields: lot_code / type / crop / qty / site / bin | Dev | 1 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.4.2 | Lot status workflow (Draft → Shipped/Rejected) | Dev | 0.5 | 2.4.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.4.3 | Server-side validation: site required; mass-balance | Dev | 0.5 | 2.4.2 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.5 | Transfer DocType | Dev | 1.5 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.6 | ScaleTicket DocType | Dev | 1 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.7 | QCTest DocType | Dev | 1 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.8 | Certificate DocType | Dev | 1 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.9 | Nonconformance DocType | Dev | 1 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.10 | EvidencePack DocType (stub) | Dev | 1 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.11 | Complaint DocType | Dev | 0.5 | 2.4 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.12 | Observation DocType | Dev | 1.5 | 2.3 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.13 | RBAC + Site Isolation | Dev | 2 | 2.1–2.12 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.13.1 | Role Profiles (YAM Farm Ops / Warehouse / QA Mgr) | Dev | 0.5 | 2.13 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.13.2 | Permission query conditions on all DocTypes | Dev | 1 | 2.13.1 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.13.3 | New user default: no site access | Dev | 0.5 | 2.13.2 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
2.14 | Phase 2 acceptance: AT-01, AT-10 | Dev | 1 | 2.1–2.13 |  | Done | 2026-02-24 | 2026-04-03 | 2026-04-03 | ✅ | ✅ | ✅ | ✅ | ✅
3 | Phase 3 — Traceability Engine |  |  |  |  | Partial | 2026-02-24 | 2026-04-17
3.1 | Transfer Split logic | Dev | 2 | 2 |  | Partial | 2026-02-24 | 2026-04-17
3.1.1 | on_submit: split parent Lot quantity | Dev | 1 | 3.1 |  | Partial | 2026-02-24 | 2026-04-17
3.1.2 | Mass-balance enforcement | Dev | 0.5 | 3.1.1 |  | Partial | 2026-02-24 | 2026-04-17
3.1.3 | Unit tests for split controller | Dev | 0.5 | 3.1.2 |  | Partial | 2026-02-24 | 2026-04-17
3.2 | Transfer Merge logic | Dev | 1.5 | 3.1 |  | Partial | 2026-02-24 | 2026-04-17
3.3 | Transfer Blend logic | Dev | 1 | 3.2 |  | Partial | 2026-02-24 | 2026-04-17
3.4 | Backward Trace view | Dev | 2 | 3.1–3.3 |  | Partial | 2026-02-24 | 2026-04-17
3.4.1 | Recursive query: walk parent_lot upstream | Dev | 1 | 3.4 |  | Partial | 2026-02-24 | 2026-04-17
3.4.2 | Script Report: Lot Backward Trace | Dev | 0.5 | 3.4.1 |  | Partial | 2026-02-24 | 2026-04-17
3.4.3 | Show QC/cert/bin history per ancestor | Dev | 0.5 | 3.4.2 |  | Partial | 2026-02-24 | 2026-04-17
3.5 | Forward Trace view | Dev | 1.5 | 3.1–3.3 |  | Partial | 2026-02-24 | 2026-04-17
3.6 | Phase 3 acceptance: AT-03, AT-04, AT-05 | Dev | 1 | 3.1–3.5 |  | Partial | 2026-02-24 | 2026-04-17
4 | Phase 4 — QA/QC Controls + Season Policy |  |  |  |  | Not Started | 2026-02-24
4.1 | QCTest form validation | Dev | 1 | 3 |  | Not Started | 2026-02-24
4.1.1 | Pass/fail auto-calc from thresholds | Dev | 0.5 | 4.1 |  | Not Started | 2026-02-24
4.1.2 | Mandatory test check per Season Policy | Dev | 0.5 | 4.1.1 |  | Not Started | 2026-02-24
4.2 | Certificate expiry enforcement | Dev | 1 | 3 |  | Not Started | 2026-02-24
4.2.1 | Scheduled job: flag expired certs daily | Dev | 0.5 | 4.2 |  | Not Started | 2026-02-24
4.2.2 | Lot submit validator: reject if cert expired | Dev | 0.5 | 4.2.1 |  | Not Started | 2026-02-24
4.3 | Season Policy DocType | Dev | 1.5 | 2 |  | Not Started | 2026-02-24
4.3.1 | Fields: crop / season / mandatory_tests / certs | Dev | 0.5 | 4.3 |  | Not Started | 2026-02-24
4.3.2 | Sample fixtures (wheat / barley policies) | Dev | 0.5 | 4.3.1 |  | Not Started | 2026-02-24
4.3.3 | Policy lookup from Lot submit controller | Dev | 0.5 | 4.3.2 |  | Not Started | 2026-02-24
4.4 | Shipment gating controller | Dev | 1.5 | 4.1–4.3 |  | Not Started | 2026-02-24
4.4.1 | Server-side: block submit if policy not satisfied | Dev | 1 | 4.4 |  | Not Started | 2026-02-24
4.4.2 | Error message lists missing QC / expired certs | Dev | 0.5 | 4.4.1 |  | Not Started | 2026-02-24
4.5 | CAPA workflow (Nonconformance) | Dev | 1 | 2.9 |  | Not Started | 2026-02-24
4.6 | Certificate management UI (filter by expiry) | Dev | 0.5 | 4.2 |  | Not Started | 2026-02-24
4.7 | Phase 4 acceptance: AT-02, AT-06 | Dev | 1 | 4.1–4.6 |  | Not Started | 2026-02-24
5 | Phase 5 — Scale + Sensor Integrations |  |  |  |  | Not Started | 2026-02-24
5.1 | ScaleTicket CSV import | Dev | 2 | 4 |  | Not Started | 2026-02-24
5.1.1 | CSV parser: validate columns; reject bad rows | Dev | 0.5 | 5.1 |  | Not Started | 2026-02-24
5.1.2 | Map ticket rows to existing Lots | Dev | 0.5 | 5.1.1 |  | Not Started | 2026-02-24
5.1.3 | Update Lot quantity from net weight | Dev | 0.5 | 5.1.2 |  | Not Started | 2026-02-24
5.1.4 | Row-level error report (import log) | Dev | 0.5 | 5.1.3 |  | Not Started | 2026-02-24
5.2 | Mismatch detection → auto-Nonconformance | Dev | 1 | 5.1 |  | Not Started | 2026-02-24
5.3 | MQTT IoT Gateway | Dev | 2 | 2.12 |  | Not Started | 2026-02-24
5.3.1 | FastAPI / MQTT subscriber stub | Dev | 1 | 5.3 |  | Not Started | 2026-02-24
5.3.2 | Translate payload → Frappe REST POST Observation | Dev | 0.5 | 5.3.1 |  | Not Started | 2026-02-24
5.3.3 | Docker Compose iot-gateway service | DevOps | 0.5 | 5.3.2 |  | Not Started | 2026-02-24
5.4 | Observation quality_flag validation | Dev | 1.5 | 2.12 |  | Not Started | 2026-02-24
5.4.1 | Threshold table per metric_type + site | Dev | 0.5 | 5.4 |  | Not Started | 2026-02-24
5.4.2 | Set quality_flag = Quarantine if out-of-range | Dev | 0.5 | 5.4.1 |  | Not Started | 2026-02-24
5.4.3 | Quarantined data excluded from AI inputs | Dev | 0.5 | 5.4.2 |  | Not Started | 2026-02-24
5.5 | Critical threshold Frappe alerts | Dev | 1 | 5.4 |  | Not Started | 2026-02-24
5.6 | Phase 5 acceptance: AT-07, AT-08 | Dev | 1 | 5.1–5.5 |  | Not Started | 2026-02-24
6 | Phase 6 — AI Assist Layer (Propose-only) |  |  |  |  | Not Started | 2026-02-24
6.1 | AI Gateway FastAPI service | Dev | 2 | 5 |  | Not Started | 2026-02-24
6.1.1 | POST /suggest endpoint (3 tasks) | Dev | 1 | 6.1 |  | Not Started | 2026-02-24
6.1.2 | PII/pricing/customer-ID redaction middleware | Dev | 0.5 | 6.1.1 |  | Not Started | 2026-02-24
6.1.3 | Docker Compose ai-gateway service | DevOps | 0.5 | 6.1.2 |  | Not Started | 2026-02-24
6.2 | AI Compliance Check (FR-AI-01) | Dev | 1.5 | 6.1 |  | Not Started | 2026-02-24
6.3 | CAPA Draft suggestion (FR-AI-02) | Dev | 1 | 6.1 |  | Not Started | 2026-02-24
6.4 | EvidencePack narrative summary (FR-AI-03) | Dev | 1 | 6.1 |  | Not Started | 2026-02-24
6.5 | AI interaction logging (FR-AI-05) | Dev | 1 | 6.1 |  | Not Started | 2026-02-24
6.5.1 | Log: timestamp / rec ref / prompt hash / outcome | Dev | 0.5 | 6.5 |  | Not Started | 2026-02-24
6.5.2 | AI Log DocType (append-only) | Dev | 0.5 | 6.5.1 |  | Not Started | 2026-02-24
6.6 | AI governance tests | Dev+QA | 1 | 6.2–6.5 |  | Not Started | 2026-02-24
6.7 | Ollama local LLM integration (offline, optional) | Dev | 1 | 6.1 |  | Not Started | 2026-02-24
7 | Phase 7 — EvidencePack Generator |  |  |  |  | Not Started | 2026-02-24
7.1 | EvidencePack builder controller | Dev | 2 | 6 |  | Not Started | 2026-02-24
7.1.1 | Collect QC / certs / tickets / obs / NCs in scope | Dev | 1 | 7.1 |  | Not Started | 2026-02-24
7.1.2 | Link documents to EvidencePack child table | Dev | 0.5 | 7.1.1 |  | Not Started | 2026-02-24
7.1.3 | Status: Draft → Ready → Sent | Dev | 0.5 | 7.1.2 |  | Not Started | 2026-02-24
7.2 | PDF export (Jinja2 print format) | Dev | 1.5 | 7.1 |  | Not Started | 2026-02-24
7.3 | ZIP export (bundle linked file attachments) | Dev | 1 | 7.1 |  | Not Started | 2026-02-24
7.4 | Auditor read-only portal view (stub for V1.2) | Dev | 0.5 | 7.1 |  | Not Started | 2026-02-24
7.5 | Phase 7 acceptance: AT-09 | Dev+QA | 1 | 7.1–7.4 |  | Not Started | 2026-02-24
8 | Phase 8 — Staging (k3s) |  |  |  |  | Not Started | 2026-02-24
8.1 | k3s single-node setup | DevOps | 1 | 7 |  | Not Started | 2026-02-24
8.1.1 | Provision server; k3s install | DevOps | 0.5 | 8.1 |  | Not Started | 2026-02-24
8.1.2 | Storage class + persistent volumes | DevOps | 0.5 | 8.1.1 |  | Not Started | 2026-02-24
8.2 | WireGuard VPN | DevOps | 1 | 8.1 |  | Not Started | 2026-02-24
8.3 | Kubernetes manifests / Helm chart | DevOps | 2 | 8.1 |  | Not Started | 2026-02-24
8.3.1 | Helm chart: all services | DevOps | 1.5 | 8.3 |  | Not Started | 2026-02-24
8.3.2 | Secrets via k3s Secrets (never plaintext) | DevOps | 0.5 | 8.3.1 |  | Not Started | 2026-02-24
8.4 | Data migration: dev → staging | DevOps | 1 | 8.3 |  | Not Started | 2026-02-24
8.5 | All 10 acceptance tests on staging | Dev+QA | 2 | 8.1–8.4 |  | Not Started | 2026-02-24
9 | Phase 9 — V1.1 Release |  |  |  |  | Not Started | 2026-02-24
9.1 | Release notes (12_RELEASE_NOTES.md) | Dev | 0.5 | 8 |  | Not Started | 2026-02-24
9.2 | Final documentation review | Dev+QA | 1 | 8 |  | Not Started | 2026-02-24
9.2.1 | Review all 12 Docs v1.1 documents | Dev | 0.5 | 9.2 |  | Not Started | 2026-02-24
9.2.2 | Update SRS change log | Dev | 0.5 | 9.2.1 |  | Not Started | 2026-02-24
9.3 | Owner sign-off meeting | Owner | 0.5 | 9.1–9.2 |  | Not Started | 2026-02-24
9.4 | GitHub release tag v1.1.0 | DevOps | 0.5 | 9.3 |  | Not Started | 2026-02-24
9.5 | Team briefing + staging access grant | Owner | 0.5 | 9.4 |  | Not Started | 2026-02-24
TOTAL (V1.1 delivery phases) |  | ≈ 105 dev-days |  |  |  | Not Started | 2026-02-24

## Gantt
Phase | Task / Work Package | Owner | W1 23 Feb | W2 02 Mar | W3 09 Mar | W4 16 Mar | W5 23 Mar | W6 30 Mar | W7 06 Apr | W8 13 Apr | W9 20 Apr | W10 27 Apr | W11 04 May | W12 11 May | W13 18 May | W14 25 May | W15 01 Jun | W16 08 Jun | W17 15 Jun | W18 22 Jun | W19 29 Jun | W20 06 Jul
Ph0 | Docker Compose + run.sh | DevOps
Ph0 | Frappe + ERPNext install | DevOps
Ph0 | Acceptance: env AT | DevOps
| ── MILESTONE M0: Dev env live ── |  |  | ◆
Ph1 | bench new-app + hooks + workspace | Dev
Ph1 | CI/CD pipeline | DevOps
Ph1 | Acceptance: app installs, CI green | DevOps
| ── MILESTONE M1: App scaffold live ── |  |  |  | ◆
Ph2 | Site + StorageBin + Device DocTypes | Dev
Ph2 | Lot + Transfer + ScaleTicket DocTypes | Dev
Ph2 | QCTest + Certificate + NC DocTypes | Dev
Ph2 | EvidencePack + Complaint + Obs DocTypes | Dev
Ph2 | RBAC + Site Isolation | Dev
Ph2 | Acceptance: AT-01, AT-10 | Dev
| ── MILESTONE M2: 12 DocTypes live ── | [6 empty] | ◆
Ph3 | Transfer Split / Merge / Blend ctrl | Dev
Ph3 | Backward + Forward trace views | Dev
Ph3 | Acceptance: AT-03, AT-04, AT-05 | Dev
| ── MILESTONE M3: Traceability ✓ ── | [8 empty] | ◆
Ph4 | QCTest validation + Season Policy | Dev
Ph4 | Shipment gate + CAPA workflow | Dev
Ph4 | Acceptance: AT-02, AT-06 | Dev+QA
| ── MILESTONE M4: QA/QC gate ✓ ── | [10 empty] | ◆
Ph5 | ScaleTicket CSV import | Dev
Ph5 | MQTT IoT Gateway | Dev
Ph5 | Observation quality_flag + alerts | Dev
Ph5 | Acceptance: AT-07, AT-08 | Dev
| ── MILESTONE M5: Scale+Sensor ✓ ── | [12 empty] | ◆
Ph6 | AI Gateway FastAPI service | Dev
Ph6 | Compliance check + CAPA draft + log | Dev
Ph6 | AI governance tests (FR-AI-04–06) | Dev+QA
| ── MILESTONE M6: AI Assist live ── | [14 empty] | ◆
Ph7 | EvidencePack builder | Dev
Ph7 | PDF + ZIP export | Dev
Ph7 | Acceptance: AT-09 | Dev+QA
| ── MILESTONE M7: EvidencePack ✓ ── | [15 empty] | ◆
Ph8 | k3s node setup + WireGuard VPN | DevOps
Ph8 | Helm chart + data migration | DevOps
Ph8 | All 10 AT on k3s staging | Dev+QA
| ── MILESTONE M8: Staging passes ── | [18 empty] | ◆
Ph9 | Release notes + doc review | Dev
Ph9 | Owner sign-off | Owner
Ph9 | GitHub tag v1.1.0 | DevOps
| ── MILESTONE M9: V1.1 RELEASED 🎉 ── | [20 empty] | ◆
Doc | Documentation stream (parallel) | Dev+QA
LEGEND
| Active work |  | Review / buffer |  | Docs (parallel) |  | Milestone

## Backlog
Idea ID | Stage | Supply Chain Phase | Feature Name | AI Mode | Actionability | KPIs | Target Release
AGR-CEREAL-001 | A | Pre-season Planning | Crop/Variety Selection | Optimization + Prediction | Propose-only | Margin/ha; Yield/ha; Rotation compliance | V1.3
AGR-CEREAL-002 | A | Pre-season Planning | Fertility Plan Optimization | Optimization | Propose-only | Nutrient efficiency; Cost/ha; Yield stability | V1.3
AGR-CEREAL-003 | A | Pre-season Planning | Planting Window Prediction | Prediction | Propose-only | On-time planting %; Yield delta; Replant rate | V1.3
AGR-CEREAL-004 | A | Pre-season Planning | Planning Impact Simulation | Simulation | Read-only | CO2e/ton; Soil health proxy; Audit readiness | V1.3
AGR-CEREAL-005 | A | Pre-season Planning | Acreage Aggregation Forecast | Forecasting | Read-only | Acreage forecast error; Downstream stockouts | V1.3
AGR-CEREAL-006 | A | Pre-season Planning | Budget Scenario Engine | Simulation | Read-only | Budget variance; ROI accuracy | V1.3
AGR-CEREAL-007 | A | Pre-season Planning | Irrigation Feasibility & Plan | Optimization + Prediction | Propose-only | Water use efficiency; Stress days reduced | V1.3
AGR-CEREAL-008 | A | Pre-season Planning | Disease-Resistant Variety Reco | Prediction | Propose-only | Disease incidence; Fungicide cost reduction | V1.3
AGR-CEREAL-009 | A | Pre-season Planning | Field Accessibility Risk | Prediction | Propose-only | Delay days; Compaction events | V1.3
AGR-CEREAL-010 | A | Pre-season Planning | Geo-Regulatory Input Flags | RAG-docs + Rules | Read-only | Violations prevented; Audit pass rate | V1.3
AGR-CEREAL-011 | B | Input Procurement | Input Demand Forecast | Forecasting | Propose-only | Stockout %; Excess inventory $; Service level | V1.3
AGR-CEREAL-012 | B | Input Procurement | Supplier Risk Scoring | Risk scoring | Propose-only | Defect rate; Delivery reliability; Loss prevention | V1.3
AGR-CEREAL-013 | B | Input Procurement | Forward Buying Scenarios | Simulation | Read-only | Cost savings; Hedge effectiveness | V1.3
AGR-CEREAL-014 | B | Input Procurement | Receiving Match Automation | Document AI + Anomaly | Execute-with-approval | Receiving cycle time; Mismatch rate; Expiry incidents | V1.3
AGR-CEREAL-015 | B | Input Procurement | SDS & Restricted Use Validation | RAG-docs | Read-only | Violations prevented; Audit readiness | V1.3
AGR-CEREAL-016 | B | Input Procurement | Deliveries vs Field Schedule | Optimization | Propose-only | Idle time; Missed windows | V1.3
AGR-CEREAL-017 | B | Input Procurement | RFQ Comparison Copilot | Copilot | Propose-only | Cycle time; Contract quality; Savings | V1.3
AGR-CEREAL-018 | B | Input Procurement | Fair Input Allocation | Optimization | Propose-only | Allocation satisfaction; Yield loss avoided | V1.3
AGR-CEREAL-019 | C | Field Ops & Planting | Planter Calibration Anomaly | Anomaly detection | Execute-with-approval | Emergence uniformity; Replant %; Yield delta | V1.3
AGR-CEREAL-020 | C | Field Ops & Planting | Work Orders & Notes Copilot | Copilot | Propose-only | Documentation completeness; Audit pass rate | V1.3
AGR-CEREAL-021 | C | Field Ops & Planting | Crew & Machine Scheduling | Optimization | Propose-only | Utilization; Overtime; On-time ops % | V1.3
AGR-CEREAL-022 | C | Field Ops & Planting | Compaction Risk Advisor | Prediction | Propose-only | Soil damage events; Delay days | V1.3
AGR-CEREAL-023 | C | Field Ops & Planting | Fuel/Parts Stock Forecast | Forecasting | Propose-only | Downtime; Emergency purchases | V1.3
AGR-CEREAL-024 | C | Field Ops & Planting | Seed Lot Capture | Workflow automation | Execute-with-approval | Traceability completeness; Recall time reduction | V1.3
AGR-CEREAL-025 | C | Field Ops & Planting | Stand Count via Vision | Vision | Read-only | Detection speed; Replant decision accuracy | V1.3
AGR-CEREAL-026 | C | Field Ops & Planting | Deviation Impact Analytics | Analytics copilot | Read-only | Variance visibility; Corrective actions taken | V1.3
AGR-CEREAL-027 | C | Field Ops & Planting | Safety Incident Risk | Risk prediction | Propose-only | Incident rate; Near-miss closure time | V1.3
AGR-CEREAL-028 | D | In-season Crop Mgmt | Stress-to-Prescription | Vision + Decision support | Propose-only | Response time; Yield loss avoided | V1.2
AGR-CEREAL-029 | D | In-season Crop Mgmt | Disease Identification | Vision | Propose-only | Diagnosis accuracy; Fungicide ROI | V1.2
AGR-CEREAL-030 | D | In-season Crop Mgmt | Irrigation Optimizer | Optimization | Execute-with-approval | Water savings; Stress days reduced | V1.2
AGR-CEREAL-031 | D | In-season Crop Mgmt | Variable Rate Nitrogen | Optimization + Explainability | Propose-only | Protein targets hit; N efficiency | V1.2
AGR-CEREAL-032 | D | In-season Crop Mgmt | Pest Outbreak Predictor | Prediction | Propose-only | Detection lead time; Yield loss avoided | V1.2
AGR-CEREAL-033 | D | In-season Crop Mgmt | Localized Recommendations | RAG-docs + Prediction | Propose-only | Adoption rate; Performance uplift | V1.2
AGR-CEREAL-034 | D | In-season Crop Mgmt | Spray Timing Advisor | Prediction + Rules | Propose-only | Efficacy; Drift incidents; Re-spray rate | V1.2
AGR-CEREAL-035 | D | In-season Crop Mgmt | Calibrated Yield Forecast | Probabilistic forecasting | Read-only | Forecast error; Usefulness score | V1.2
AGR-CEREAL-036 | D | In-season Crop Mgmt | Loss Assessment Assist | Vision + Anomaly | Propose-only | Claim cycle time; Dispute rate | V1.2
AGR-CEREAL-037 | D | In-season Crop Mgmt | Soil Health Tracking | Analytics + Estimation | Read-only | Reporting cycle time; Data completeness | V1.2
AGR-CEREAL-038 | D | In-season Crop Mgmt | Alert Ranking | Alert ranking | Read-only | Alert action rate; False alert rate | V1.2
AGR-CEREAL-039 | D | In-season Crop Mgmt | Data Quality Guardrails | Anomaly + Data validation | Execute-with-approval | Data error rate; Model stability | V1.2
AGR-CEREAL-040 | E | Harvest Operations | Harvest Window Predictor | Prediction | Propose-only | Losses avoided; Drying cost reduction | V1.2
AGR-CEREAL-041 | E | Harvest Operations | Combine Settings Optimizer | Optimization | Propose-only | Loss %; Throughput; Fuel/ton | V1.2
AGR-CEREAL-042 | E | Harvest Operations | Harvest-to-Truck Dispatch | Dispatch optimization | Execute-with-approval | Idle time; Turnaround time | V1.2
AGR-CEREAL-043 | E | Harvest Operations | Mycotoxin Risk Flags | Prediction + Anomaly | Propose-only | Contamination incidents; Rejected loads | V1.2
AGR-CEREAL-044 | E | Harvest Operations | Yield Map Insights | Analytics copilot | Propose-only | Action adoption; Next-season uplift | V1.2
AGR-CEREAL-045 | E | Harvest Operations | Harvest Predictive Maintenance | Predictive maintenance | Propose-only | Unplanned downtime; Repair cost | V1.2
AGR-CEREAL-046 | E | Harvest Operations | Harvest Cost Visibility | Analytics automation | Read-only | Cost visibility latency; Margin variance | V1.2
AGR-CEREAL-047 | E | Harvest Operations | Silo Intake Scheduling | Scheduling optimization | Execute-with-approval | Queue time; Reject rate | V1.2
AGR-CEREAL-048 | F | Storage Management | Aeration Control | Anomaly + Control optimization | Execute-with-approval | Spoilage %; Energy cost; Hotspot incidents | V1.2
AGR-CEREAL-049 | F | Storage Management | Blend Optimization | Optimization | Propose-only | Contract compliance %; Revenue/ton | V1.2
AGR-CEREAL-050 | F | Storage Management | Shrink/Theft Detection | Anomaly detection | Read-only | Shrink %; Detection lead time | V1.2
AGR-CEREAL-051 | F | Storage Management | Storage Inspection Copilot | Copilot + Checklist | Propose-only | Inspection completeness; Findings reduced | V1.2
AGR-CEREAL-052 | F | Storage Management | Inventory Reconciliation | Anomaly + Automation | Execute-with-approval | Reconciliation time; Adjustment rate | V1.2
AGR-CEREAL-053 | F | Storage Management | Moisture Out-of-Spec Predictor | Prediction | Propose-only | Rework reduced; Spec compliance | V1.2
AGR-CEREAL-054 | F | Storage Management | Capacity Constraint Feedback | Constraint optimization | Propose-only | Overflow events; Emergency transport cost | V1.2
AGR-CEREAL-055 | F | Storage Management | IoT Security Monitoring | Security anomaly | Read-only | Incident rate; Time-to-detect | V1.2
AGR-CEREAL-056 | G | Logistics & Trading | Routing with Constraints | Optimization | Execute-with-approval | On-time %; Cost/ton-km | V2.0
AGR-CEREAL-057 | G | Logistics & Trading | Export Docs Automation | Document AI | Execute-with-approval | Doc error rate; Cycle time | V2.0
AGR-CEREAL-058 | G | Logistics & Trading | Freight Billing Anomalies | Anomaly detection | Propose-only | Dispute rate; Overpayment prevented | V2.0
AGR-CEREAL-059 | G | Logistics & Trading | In-transit Quality Risk | Anomaly + Prediction | Propose-only | Rejected loads; Claims reduced | V2.0
AGR-CEREAL-060 | G | Logistics & Trading | Cargo Theft/Diversion | Anomaly detection | Read-only | Theft incidents; Detection lead time | V2.0
AGR-CEREAL-061 | G | Logistics & Trading | Shipment Carbon Reporting | Estimation + Reporting automation | Read-only | Reporting cycle time; Auditability | V2.0
AGR-CEREAL-062 | G | Logistics & Trading | Exception Management Copilot | Workflow copilot | Propose-only | Resolution time; Service level | V2.0
AGR-CEREAL-063 | H | Processing & Mfg | Incoming Lot Classification | Classification + Anomaly | Execute-with-approval | Reject accuracy; Contamination incidents | V2.0
AGR-CEREAL-064 | H | Processing & Mfg | Process Parameter Optimization | Optimization | Propose-only | Yield; Energy/ton; Throughput | V2.0
AGR-CEREAL-065 | H | Processing & Mfg | Packaging Line PdM | Predictive maintenance | Propose-only | Downtime; Defect rate | V2.0
AGR-CEREAL-066 | H | Processing & Mfg | HACCP Evidence Builder | RAG-docs + Evidence automation | Read-only | Audit prep time; Findings reduced | V2.0
AGR-CEREAL-067 | H | Processing & Mfg | Batch Scheduling with Constraints | Scheduling optimization | Propose-only | Throughput; Changeover time; OEE | V2.0
AGR-CEREAL-068 | H | Processing & Mfg | Formulation Optimizer | Optimization + Simulation | Propose-only | Time-to-formulate; Quality pass rate | V2.0
AGR-CEREAL-069 | H | Processing & Mfg | Label/Allergen Compliance | Rules + Document AI | Execute-with-approval | Label compliance; Recall prevention | V2.0
AGR-CEREAL-070 | H | Processing & Mfg | Yield Loss RCA Copilot | Analytics copilot | Read-only | Yield variance explained; Corrective action rate | V2.0
AGR-CEREAL-071 | H | Processing & Mfg | Provenance Query during Incidents | Traceability graph + RAG | Read-only | Time-to-trace; Containment time | V2.0
AGR-CEREAL-072 | I | Customer & Market | Retail Demand Forecast | Forecasting | Read-only | Forecast error; Stockouts %; Waste % | V2.1+
AGR-CEREAL-073 | I | Customer & Market | Allocation Optimization | Optimization | Propose-only | Service level; Transport cost | V2.1+
AGR-CEREAL-074 | I | Customer & Market | Expiry Waste Predictor | Prediction | Propose-only | Waste %; Markdown effectiveness | V2.1+
AGR-CEREAL-075 | I | Customer & Market | Pricing & Promo Optimizer | Optimization | Propose-only | Margin; Volume; Promo ROI | V2.1+
AGR-CEREAL-076 | I | Customer & Market | Complaint-to-Lot Linkage | NLP + Traceability | Read-only | Time-to-trace; Repeat complaint rate | V2.1+
AGR-CEREAL-077 | I | Customer & Market | Fill-rate Anomaly Monitor | Anomaly detection | Read-only | Fill-rate; Late orders | V2.1+
AGR-CEREAL-078 | I | Customer & Market | Recall Execution Automation | Workflow automation | Execute-with-approval | Time-to-remove; % units recovered | V2.1+
AGR-CEREAL-079 | I | Customer & Market | Assortment Optimization | Analytics + Clustering | Propose-only | Sales lift; OOS reduction | V2.1+
AGR-CEREAL-080 | I | Customer & Market | End-to-End Margin Copilot | Analytics copilot | Read-only | Margin visibility time; Leakage recovered | V2.1+

## Milestones
Milestone | Target Date | Week | Description | Exit Criteria | Status
M0 | 2026-03-06 | W2 | Dev environment live | Docker Compose starts; Frappe login works; RAM ≤ 6 GB | ✅ Done
M1 | 2026-03-13 | W3 | App scaffold installed; CI green | `yam_agri_core` app installs; lint + secret scan pass | ✅ Done
M2 | 2026-04-03 | W6 | All 12 DocTypes live; site isolation | AT-01 (create records) and AT-10 (site isolation) pass | ✅ Done
M3 | 2026-04-17 | W8 | Traceability engine complete | AT-03 (split), AT-04 (backward trace), AT-05 (forward trace) pass | 🟨 In Progress
M4 | 2026-05-01 | W10 | QA/QC + Season Policy gate live | AT-02 (QCTest + cert) and AT-06 (shipment gate) pass | ⬜ Pending
M5 | 2026-05-15 | W12 | Scale + Sensor integrations | AT-07 (CSV import + NC) and AT-08 (quarantine + alert) pass | ⬜ Pending
M6 | 2026-05-29 | W14 | AI Assist layer running (propose-only) | AI suggestions visible; FR-AI-04–06 governance tests pass | ⬜ Pending
M7 | 2026-06-05 | W15 | EvidencePack generator | AT-09 (evidence pack for date range + site) passes | ⬜ Pending
M8 | 2026-06-26 | W18 | All 10 AT pass on k3s staging | Every acceptance test green on staging node | ⬜ Pending
M9 | 2026-07-10 | W20 | V1.1 RELEASED — owner sign-off | GitHub tag v1.1.0; release notes published; owner signs off | ⬜ Pending